## Pending (No Integration)
Pending items buildable NOW — without integrations (mock data / Now Assist)
Priority | Area | Pending item (buildable now) | How to do it now – no integration (mock data / Now Assist) | BRD/FSD Ref | Effort
P1 | Compare & Match | Tier 2 fuzzy match: fuzzy counterparty-name + notional tolerance band + value-date ±N window | Extend CompareMatch against the seeded PCM booking table – no live PCM needed | FR-MTH-010/013 | M
P1 | Compare & Match | Value-date business-day tolerance (exclude weekends + holidays) | Use a static/config holiday list as a stand-in for Takara/Thomas Murray | FR-MTH-011 | S
P1 | Compare & Match | Candidate ranking (smallest diff; +ve before -ve) + surface top candidates | Pure logic on booking-table results | FR-MTH-012 | S
P1 | Compare & Match | Tier 3 counterparty-less search | Drop CP filter, search remaining fields on booking table | FR-MTH-020/021 | S
P1 | Compare & Match | Multiple-candidate handling (surface all with deltas; analyst selects) | Return list + selection UI | FR-MTH-005 | M
P1 | Compare & Match | Matched-but-Settled as a distinct exception type + flow | Read booking status; branch the outcome | FR-MTH-004/WRB-006 | S
P1 | Compare & Match | Netting: process each leg independently | Per-cashflow already; add leg awareness | FR-MTH-023 | S
P1 | Wizard | Wire wizard Run → real Compare & Match vs target (field-by-field + confidence + mismatches) | Feed record-mode rows into CompareMatch against mock target | FR-3.5/4.4/4.5 | M
P1 | Extraction/AI | Per-field confidence scores + LOW_CONFIDENCE flags (identify / extract / match) | Now Assist can return confidence; surface a flag in UI | FR-EXT-007/008 | M
P1 | RBAC | Roles + ACLs: analyst / manager / admin (record + field ACLs) | Native ServiceNow roles & ACLs; SSO mapping deferred | FR-RBAC-001/002/004 | M
P1 | RBAC/Wizard | Per-analyst assignment + scoped visibility (analysts see only assigned) | Assignment table keyed to ServiceNow users | FR-1.3/RBAC-003/2.5/5.2 | M
P1 | Audit | Append-only audit trail (AI inference: model/prompt/confidence/reasoning + override original-vs-corrected) | New audit table + capture at each step | FR-AUD-001..006/EXT-009 | L
P1 | GUI | Dashboard buckets Open / Critical / Resolved; sort value-desc then ageing; ageing→Critical | Compute from record dates/values – all local | FR-UI-001/002/003 | M
P2 | Identification | AI classifier: SSI_Verification / Confirmation_Reaffirmation + confidence + threshold routing | Build as a Now Assist skill (same stack we used) | FR-ID-010..017 | M
P2 | Identification | Structural filter rules on .eml (In-Reply-To / Re: / Fwd: newly-initiated; bounce; OOO) | Header parsing on the dropped .eml – no mailbox needed | FR-ID-002..005 | S
P2 | Tagging/Assign | Analyst assignment engine (alphabet-wise CP→analyst) + internal state incl analyst-id | Internal assignment + state; Outlook write stays deferred | FR-TAG-003/004/005/010-012 | M
P2 | Admin config | Admin config store + panel (routing %, thresholds, tolerances, ageing, allocation map) | Config table + simple admin UI – fully local | §17 / FR-UI-030 | M
P2 | Wizard | Version auto-increment on re-publish; unpublish; work-driver/activity filters | Add version logic + re-add filter chips | FR-2.4/5.1/2.2 | S
P2 | Wizard | Calculated/derived fields; up-to-5 target cap; per-field info tooltips | Builder UI enhancements | FR-3.3/3.6 | M
P2 | GUI | Full processing-trail view per cashflow (ingest→identify→extract→confirm→match→action) | Render from the new audit trail | FR-UI-006 | M
P2 | Confirmation | Override-capture UI + bulk-confirm child records | Extend case screen; write to audit | C5 / UC-06 | S
P2 | Audit | Config-change audit (old/new/actor/effective-from); not-retroactive to in-flight | Fires from the admin config store | FR-AUD-005/AIQ-003 | S
P2 | Write-back | Write-back audit + failure keeps cashflow in queue | Local write-back to booking/cashflow record | FR-WRB-007/008 | S
P2 | Controls | 4-eye / value-threshold internal control gate | Gate on value even with mock downstream | FR-WRB-003 | M
P2 | Ingestion | Routing % throttle model (config-driven; applies to current ingestion) | Percentage split logic; no live mailbox needed | FR-RTE-001/003/004 | S
P3 | Extraction | Non-English extraction (German / Japanese) | Prompt handles it; add to generic skill | FR-EXT-003 | S
P3 | Extraction | Attachment handling: multi-attachment selection, corrupt/zero-byte flag, trade-vs-SSI classify | Logic on the embedded attachments in the .eml | FR-EXT-023/025/026 | M
P3 | Extraction | Configurable column-to-field mapping (Excel) + unit scaling (millions/thousands) | Config-driven mapping in the xlsx extractor | FR-EXT-021/022 | S
P3 | Extraction | Parent-email roll-up state (resolved when all children terminal) + mixed-status display | Compute parent state from children | FR-EXT-033/UC-15 | S
P3 | Errors | ERROR queue state on processing failure; per-cashflow failure isolation | Add ERROR status + surface in dashboard | ERR-002/NFR-004 | S
P3 | AI quality | AI performance metrics view (classifier/extractor/matcher) + basic drift from overrides | Reuse the AI-vs-deterministic 'Match' signal; add counts | §16.3/FR-AIQ-010 | M
P3 | GUI | Credit-compliance badge as a mock field | Placeholder field until Takara integration | FR-UI-007 (mock) | S
P3 | Ingestion | Duplicate-email detection (Message-ID) – formalise the existing guard | Already partially present; make explicit (BRD defers to P2) | FR-ING-006 | S
Total buildable-now items: 33 (P1=13, P2=12, P3=8) · Effort: S=small, M=medium, L=large
Excluded — requires integration (parked until connectivity is available):
• Live Outlook / Microsoft Graph mailbox polling + Outlook category tag write (FR-ING-001..005, FR-TAG-002)
• NEWS read + real write-back (INT-002, FR-WRB-002 real target)
• PCM real read/write (INT-003 – currently mocked by the seeded booking table)
• Live Eve / RDM counterparty master + alias (INT-004 – currently a local stand-in)
• Takara: live credit-compliance + holiday calendars (INT-005, FR-MTH-011 live, FR-UI-007 live)
• Chinou API (INT-006 – substituted by ServiceNow Now Assist)
• Nomura SSO role mapping (INT-007, FR-RBAC-001 SSO part)

## Part A - Compare & Match
Part A — OTC Allege Pilot: Compare & Match core (BRD §7 / FSD C1–C7)
Area / Group | Ref (FSD/BRD) | Task / Requirement | What's built (POC) | Status | % Done | Gap / Notes
C1 Email Ingestion | FR-ING-001 | Monitor OTC Settlements shared mailbox on a polling interval | Emails arrive via .eml drop → Flow trigger → record create | Partial | 45 | Live Outlook/Graph mailbox polling not built (drop-triggered)
C1 Email Ingestion | FR-ING-002 | Configurable polling interval (pilot 60m / prod 15m) via Admin | — | None | 0 | No admin-configurable interval
C1 Email Ingestion | FR-ING-003 | Retrieve all emails since last successful poll | Per-drop processing | Partial | 45 | No incremental poll window
C1 Email Ingestion | FR-ING-004 | Retry with back-off (3x) + ops alert on failure | — | None | 0 | No retry/alert
C1 Email Ingestion | FR-ING-005 | Persist last-successful-poll timestamp durably | — | N/A |  | Not applicable to drop model
C1 Email Ingestion | FR-ING-006 | Duplicate email detection (same Message-ID) [Phase 2] | App has message-id / trade-id idempotency guards | Deferred |  | Phase 2 per BRD; basic dedup already present
C1 Email Ingestion | FR-RTE-001 | Routing % controller (0-100) new-solution vs manual | — | None | 0 | No routing throttle
C1 Email Ingestion | FR-RTE-002 | Non-routed emails not tagged/modified | — | N/A |  | Depends on routing controller
C1 Email Ingestion | FR-RTE-003 | Routing changes logged with effective-from + admin id | — | None | 0 | No config audit
C1 Email Ingestion | FR-RTE-004 | Instant 0% (rollback) / 100% (cut-over) switch | — | None | 0 | No routing switch
C2 Email Identification | FR-ID-001 | Drop emails from @nomura.com; log drop | Sender-domain relevance filter (Relevant/Irrelevant) | Partial | 45 | Domain filter exists; drop-reason logging basic
C2 Email Identification | FR-ID-002 | Detect newly-initiated thread (no In-Reply-To; no Re:/Fwd:) | — | None | 0 | No thread-header rule
C2 Email Identification | FR-ID-003 | Drop replies on existing threads | — | None | 0 | Not implemented
C2 Email Identification | FR-ID-004 | Drop bounce-backs (NDR / X-Failed-Recipients) | — | None | 0 | Not implemented
C2 Email Identification | FR-ID-005 | Drop Out-of-Office auto-replies | — | None | 0 | Not implemented
C2 Email Identification | FR-ID-010 | AI classifier: SSI_VERIFICATION / CONFIRMATION_REAFFIRMATION | Deterministic SSI-only heuristic in extractor | Low | 20 | No AI classifier for the two labels
C2 Email Identification | FR-ID-011 | Return label + confidence (0-1) | — | None | 0 | No confidence score
C2 Email Identification | FR-ID-012 | SSI ≥ threshold → tag, do not advance | status 'ssi_only' halts extraction | Partial | 45 | No threshold/confidence
C2 Email Identification | FR-ID-013 | Reaffirmation ≥ threshold → tag, do not advance | — | None | 0 | Not implemented
C2 Email Identification | FR-ID-014 | Both below threshold → advance to extraction (default) | Relevant mails advance to extraction | Partial | 45 | Default path works; no threshold logic
C2 Email Identification | FR-ID-015 | No Allege label at identification (matcher decides) | Allege = matcher no-candidate outcome | Done | 100 | Matches BRD design
C2 Email Identification | FR-ID-016 | Capture model/prompt/hash/label/confidence in audit | Native gen-AI log captures AI calls | Partial | 45 | Not a structured identification audit
C2 Email Identification | FR-ID-017 | Classifier thresholds configurable via Admin | — | None | 0 | No admin config
C3 Outlook Tagging | FR-TAG-001 | Tag only picked emails | Internal workflow-state on record only | Partial | 45 | No Outlook tag write
C3 Outlook Tagging | FR-TAG-002 | Apply tags via service account (Outlook category write) | — | None | 0 | No Outlook integration
C3 Outlook Tagging | FR-TAG-003 | Tag = <analyst-id>, <state-label> | Workflow state label present; no analyst-id | Partial | 45 | No analyst-id component
C3 Outlook Tagging | FR-TAG-004 | Analyst assignment at first pickup (alphabet map) | — | None | 0 | No assignment engine
C3 Outlook Tagging | FR-TAG-005 | Analyst-id stable across states | — | N/A |  | Depends on assignment
C3 Outlook Tagging | FR-TAG-010/11/12 | State transitions Await-Confirm → Await-Review → Resolved-Matched/Unmatched | review_status + workflow status lifecycle in app | Partial | 45 | Internal states yes; Outlook write no
C3 Outlook Tagging | FR-TAG-013 | Tag failures non-blocking, logged | — | N/A |  | No Outlook tag path
C4 Field Extraction | FR-EXT-001 | Parse body → one structured record per trade; multi-trade child rows | EmlFieldExtractor + AiFieldExtractor → child cashflows | Done | 100 | Working, multi-trade
C4 Field Extraction | FR-EXT-002 | Handle body variations (prose/table/forwarded/reply) | SWIFT / pipe / HTML / label:value / prose / compact parsers | Strong | 80 | Broad format coverage
C4 Field Extraction | FR-EXT-003 | Handle non-English (German/Japanese) | — | None | 0 | Not specifically handled
C4 Field Extraction | FR-EXT-004 | Flag embedded image content [Phase 2] | Image/attachment-only mails skipped/flagged | Deferred |  | Phase 2
C4 Field Extraction | FR-EXT-005 | Flag portal/UI links [Phase 2] | — | Deferred |  | Phase 2
C4 Field Extraction | FR-EXT-006 | Normalise dates/amounts/ccy/rates to canonical | ISO date + amount normalisation in extractor | Done | 100 | Implemented
C4 Field Extraction | FR-EXT-007 | Confidence score (0-1) per field | — | None | 0 | No per-field confidence
C4 Field Extraction | FR-EXT-008 | Flag LOW_CONFIDENCE fields, non-blocking | — | None | 0 | No confidence flagging
C4 Field Extraction | FR-EXT-009 | Audit per field (model/prompt/source passage/value/confidence) | Gen-AI log stores prompt+response | Partial | 45 | No per-field source-passage capture
C4 Field Extraction | FR-EXT-020 | Excel .xls/.xlsx → one record per row | XlsxCashflowExtractor (auto sheet/header detect) | Done | 100 | Working
C4 Field Extraction | FR-EXT-021 | Configurable column-to-field mapping | Wide synonym map (deterministic) + wizard mapping | Partial | 45 | Not admin-configurable
C4 Field Extraction | FR-EXT-022 | Normalise millions/thousands to absolute | Numeric normalisation | Partial | 45 | Sign/format handled; unit scaling limited
C4 Field Extraction | FR-EXT-023 | Multi-attachment: select the trade-data attachment | xlsx detection + .eml vs xlsx separation | Partial | 45 | Basic selection
C4 Field Extraction | FR-EXT-024 | Password-protected attachments flagged [Phase 2] | — | Deferred |  | Phase 2
C4 Field Extraction | FR-EXT-025 | Corrupt / zero-byte attachments flagged | Best-effort skip | Partial | 45 | Limited handling
C4 Field Extraction | FR-EXT-026 | Classify trade-data vs SSI attachment | — | None | 0 | Not implemented
C4 Field Extraction | FR-EXT-030 | N trades → N child records (unique child_id + parent) | Child cashflow rows under parent email | Done | 100 | Implemented
C4 Field Extraction | FR-EXT-031 | Each child processed independently thru C5/C6/C7 | Per-cashflow flow | Done | 100 | Implemented
C4 Field Extraction | FR-EXT-032 | One child does not block siblings | Independent per-cashflow | Done | 100 | Implemented
C4 Field Extraction | FR-EXT-033 | Parent resolved only when all children terminal | Per-cashflow resolution | Partial | 45 | No explicit parent roll-up state
C5 Analyst Confirmation | BRD 7.6 | Present extracted fields to analyst before matching | Case screen shows extracted fields | Done | 100 | Implemented
C5 Analyst Confirmation | BRD 7.6 | Confirm → matcher proceeds on confirmed fields | Per-cashflow confirm gates match | Done | 100 | Implemented
C5 Analyst Confirmation | BRD 7.6 | Correct field(s); capture original vs corrected + ts + identity | Edit + save fields | Partial | 45 | Override not fully audited
C5 Analyst Confirmation | BRD 7.6 | Multi-trade: confirm each child independently | Per-cashflow confirmation | Done | 100 | Implemented
C5 Analyst Confirmation | UC-06 | Bulk-confirm multiple child records | — | None | 0 | No bulk action
C6 Compare & Match | FR-MTH-001 | Query settlement system on all confirmed economic fields; status=not_settled | CompareMatch keys on ccy+direction+value_date | Partial | 45 | Core key matches; status filter partial
C6 Compare & Match | FR-MTH-002 | Include counterparty_ref as filter when present | Reference displayed, not used as match key | Partial | 45 | Ref shown, not matched
C6 Compare & Match | FR-MTH-003 | Single not-settled candidate → MATCHED (Tier 1) | Exact match → matched | Done | 100 | Implemented
C6 Compare & Match | FR-MTH-004 | Single settled candidate → MATCHED_BUT_SETTLED | Booking status shown | Partial | 45 | Not a distinct exception type
C6 Compare & Match | FR-MTH-005 | Multiple candidates → surface all with deltas | — | None | 0 | Assumes single candidate
C6 Compare & Match | FR-MTH-006 | No Tier-1 candidate → Tier 2 | Amount-tolerance fallback | Partial | 45 | No true tier cascade
C6 Compare & Match | FR-MTH-010 | Tier 2 tolerances: fuzzy name, notional ±, value_date ±Z bd | Amount tolerance (1% / abs) only | Partial | 45 | No fuzzy name / vdate window
C6 Compare & Match | FR-MTH-011 | Business days exclude weekends + currency/bank holidays | — | None | 0 | No holiday calendars (Takara/Thomas Murray)
C6 Compare & Match | FR-MTH-012 | Rank candidates (smallest diff; +ve before -ve) | — | None | 0 | No ranking logic
C6 Compare & Match | FR-MTH-013 | Surface tier + field deltas + confidence | Banner shows diffs/missing | Partial | 45 | No tier/confidence indicator
C6 Compare & Match | FR-MTH-014 | No tolerance hit → Tier 3 | — | None | 0 | No Tier 3
C6 Compare & Match | FR-MTH-015 | Tolerances configurable per product (Admin) | — | None | 0 | Hardcoded tolerance
C6 Compare & Match | FR-MTH-020 | Tier 3 counterparty-less search | — | None | 0 | Not implemented
C6 Compare & Match | FR-MTH-021 | Tier 3 candidates always analyst-validated | — | None | 0 | Not implemented
C6 Compare & Match | FR-MTH-022 | No candidate across tiers → UNMATCHED / ALLEGE | No-match outcome produced | Done | 100 | Allege = no candidate
C6 Compare & Match | FR-MTH-023 | Netting: process each leg independently | Per-cashflow | Partial | 45 | No explicit netting handling
C7 Action & Write-back | FR-WRB-001 | No auto-resolve; analyst confirmation required for write-back | 'Pending Confirmation' until analyst confirms | Done | 100 | 100% HITL
C7 Action & Write-back | FR-WRB-002 | Confirm matched → write-back to NEWS/PCM under analyst identity | Write-back to local cashflow record | Partial | 45 | No NEWS/PCM integration
C7 Action & Write-back | FR-WRB-003 | 4-eye / maker-checker / value-threshold fire unchanged | — | None | 0 | Controls not hooked (out of solution)
C7 Action & Write-back | FR-WRB-004 | Resolve fuzzy: accept (write-back) or reject (→ unmatched) | Outcome buttons: mark matched / mismatch / no-match | Partial | 45 | Accept/reject present; no true fuzzy candidate
C7 Action & Write-back | FR-WRB-005 | Handle unmatched: record action (queried/escalated) | Step-3 draft: ask counterparty; Send → Escalated | Done | 100 | Record + draft present
C7 Action & Write-back | FR-WRB-006 | Handle MATCHED_BUT_SETTLED exception | — | Partial | 45 | Status visible; no dedicated flow
C7 Action & Write-back | FR-WRB-007 | Every write-back recorded in audit | resolution state changes stored | Partial | 45 | Not a formal write-back audit
C7 Action & Write-back | FR-WRB-008 | Write-back failure → cashflow stays in queue | — | None | 0 | No failure handling (local write)
Unified Analyst GUI | FR-UI-001 | Open / Critical / Resolved buckets | Match Status + Workflow Status columns + cards | Partial | 45 | Different bucket model
Unified Analyst GUI | FR-UI-002 | Sort value desc, then ageing asc | Sort by Mail Id (+ sortable columns) | Partial | 45 | Not value/ageing default
Unified Analyst GUI | FR-UI-003 | Promote to Critical (Eve/Takara flag or ageing) | — | None | 0 | No critical promotion
Unified Analyst GUI | FR-UI-004 | Per-cashflow key fields shown | Mail id, cashflow, trade id, cp, amount, ccy, dir, VD, tagging, elapsed, status | Strong | 80 | Most fields present
Unified Analyst GUI | FR-UI-005 | Click cashflow → detail view | Row click → case screen | Done | 100 | Implemented
Unified Analyst GUI | FR-UI-006 | Full processing trail per cashflow | Mail contents + extracted + compare + resolution | Partial | 45 | No end-to-end audit trail view
Unified Analyst GUI | FR-UI-007 | Credit compliance badge (Takara) | — | None | 0 | No Takara integration
Unified Analyst GUI | FR-UI-008 | Context-sensitive action buttons | Step 2/3 actions gated by state | Done | 100 | Implemented
SHEET COMPLETION (avg of in-scope tasks; Deferred/N-A excluded): |  |  |  |  | 40%
Tasks listed: 87 (in-scope scored: 79)

## Part B - Onboarding Wizard
Part B — Work Driver Onboarding Wizard (BRD FR-1 … FR-6)
Area / Group | Ref (FSD/BRD) | Task / Requirement | What's built (POC) | Status | % Done | Gap / Notes
FR-1 Access & landing | FR-1.1 | Role sets capabilities (mgr build; analyst execute) | Conceptual Manager vs Analyst; auth-gated | Partial | 45 | No enforced role model
FR-1 Access & landing | FR-1.2 | Manager → wizard mgmt; analyst → assigned work (1→dash, >1→cards) | Work-drivers landing with activity cards | Partial | 45 | Not role-driven landing
FR-1 Access & landing | FR-1.3 | Analysts see only assigned activities | — | None | 0 | No assignment scoping
FR-2 Wizard management | FR-2.1 | Wizards split into Published and Drafts | Published + Drafts sections | Done | 100 | Implemented
FR-2 Wizard management | FR-2.2 | Search + filter by work driver & activity | Search box present | Partial | 45 | Driver/activity filter chips removed
FR-2 Wizard management | FR-2.3 | New wizard: Create new OR Copy-and-edit existing | Create-a-wizard modal (both paths) | Done | 100 | Implemented
FR-2 Wizard management | FR-2.4 | Edit / publish / unpublish / version / delete | Edit, Publish, Save-as-draft, Delete | Partial | 45 | No unpublish / version increment
FR-2 Wizard management | FR-2.5 | Assign published wizards to analysts (directory) | — | None | 0 | No assignment
FR-3 Wizard Builder | FR-3.1 | Define: name/desc/BU/Sub-BU/work driver/activity | Step 1 Define (all fields) | Done | 100 | Implemented
FR-3 Wizard Builder | FR-3.2 | Input source: format/source/frequency + email-id rules | Step 2 with email-identification rules (context/keywords/senders/subject/exclusions) | Done | 100 | Implemented
FR-3 Wizard Builder | FR-3.3 | Target & mapping: up to 5 systems; map fields; calculated field | Add target system + per-field mapping + auto-map | Partial | 45 | No calculated fields / 5-cap
FR-3 Wizard Builder | FR-3.4 | Review: full-configuration summary | Step 4 Review + mapping table | Done | 100 | Implemented
FR-3 Wizard Builder | FR-3.5 | Run/validate: test compare on first item; field-by-field + confidence + mismatches | Step 5 REAL record-mode extraction (multi-trade) via Now Assist | Partial | 45 | Extraction real; compare-vs-target not yet
FR-3 Wizard Builder | FR-3.6 | Info tooltip per field | — | None | 0 | Tooltips removed
FR-4 Runtime engine | FR-4.1 | Identify the relevant item in the source | Email drop; basic relevance | Partial | 45 | No smart source identification
FR-4 Runtime engine | FR-4.2 | Convert unstructured input to structured JSON | Record-mode → JSON array (one row/trade) | Done | 100 | Implemented
FR-4 Runtime engine | FR-4.3 | Extract configured fields, AI-assisted | Generic prompt-parameterised skill (per-field prompt drives it) | Done | 100 | Implemented
FR-4 Runtime engine | FR-4.4 | Match extracted data vs target incl fuzzy + confidence | — | None | 0 | Match not wired into wizard runtime
FR-4 Runtime engine | FR-4.5 | Flag mismatches / exceptions for analyst | — | Partial | 45 | Extraction shown; no compare flags yet
FR-5 Publish/version/assign | FR-5.1 | Publish; re-publish increments version | Publish + draft states | Partial | 45 | No auto version increment
FR-5 Publish/version/assign | FR-5.2 | Assign by individual user from directory | — | None | 0 | No assignment
FR-6 Audit & governance | FR-6.1 | Audit wizard lifecycle (create/edit/publish/assign) | sys_updated tracking | Partial | 45 | No explicit lifecycle audit
FR-6 Audit & governance | FR-6.2 | Per-item audit trail (who did what, when) | Partial app logging + gen-AI log | Partial | 45 | Not consolidated
FR-6 Audit & governance | FR-6.3 | HITL checkpoints preserved end to end | OTC flow is fully HITL | Done | 100 | Implemented
Data requirements | BRD §8 | Supported input types (email/TRAM/PDF/Excel/shared folder) | Email + Excel | Partial | 45 | TRAM/PDF/shared-folder not built
Data requirements | BRD §8 | Structured JSON representation of extracted data | JSON rows via record mode | Done | 100 | Implemented
Data requirements | BRD §8 | Target systems configurable; each exposes match fields | System 1/2/PCM catalog (mock) | Partial | 45 | Mock target field sets
Data requirements | BRD §8 | Mapping model: input field → target / calculated field | Field mapping present | Partial | 45 | No calculated field
SHEET COMPLETION (avg of in-scope tasks; Deferred/N-A excluded): |  |  |  |  | 55%
Tasks listed: 28 (in-scope scored: 28)

## Cross-cutting
Cross-cutting — RBAC, Audit, Admin config, AI quality, Integrations
Area / Group | Ref (FSD/BRD) | Task / Requirement | What's built (POC) | Status | % Done | Gap / Notes
RBAC | FR-RBAC-001 | Role assignment via Nomura RBAC + SSO | ServiceNow auth (login) | Low | 20 | No SSO role mapping
RBAC | FR-RBAC-002 | Exactly one role per session | — | None | 0 | No role model
RBAC | FR-RBAC-003 | Analyst sees/actions only own or team queue | Auth-gated pages | Partial | 45 | No per-analyst scoping
RBAC | FR-RBAC-004 | Admin-only config changes | — | None | 0 | No admin role/config UI
RBAC | FR-RBAC-005 | Role changes traceable | — | None | 0 | Not implemented
Audit trail | FR-AUD-001 | Capture every system action + AI inference | Native sys_generative_ai_log for AI calls | Partial | 45 | App-action audit incomplete
Audit trail | FR-AUD-002 | Standard attributes (event/entity/actor/ts/before/after) | Partial via platform records | Partial | 45 | Not a unified audit
Audit trail | FR-AUD-003 | AI attributes (model/prompt/confidence/reasoning) | Gen-AI log has model/prompt/tokens | Partial | 45 | No confidence/reasoning capture
Audit trail | FR-AUD-004 | Override capture (original vs corrected + ts + id) | — | Low | 20 | Field edits saved; not audited
Audit trail | FR-AUD-005 | Config-change capture (old/new/admin/effective-from) | — | None | 0 | No config audit
Audit trail | FR-AUD-006 | Append-only, immutable | Gen-AI log is append-only | Partial | 45 | App audit not enforced immutable
Audit trail | FR-AUD-007 | AI audit retained per retention schedule | — | None | 0 | No retention policy set
Audit trail | FR-AUD-008 | Reconstruct full cashflow history | Processing trail partial in UI | Partial | 45 | No end-to-end reconstruction
Audit trail | FR-AUD-009 | Override rate queryable by CP/product/analyst | — | None | 0 | Not implemented
Admin config (§17) | routing_pct | Routing percentage config | — | None | 0 | Hardcoded/absent
Admin config (§17) | id_*_threshold | Classifier thresholds (SSI/Reaffirmation) | — | None | 0 | Absent
Admin config (§17) | ext_confidence | Extraction low-confidence threshold per field/product | — | None | 0 | Absent
Admin config (§17) | t2_tolerances | Tier-2 notional / value-date tolerances per product | Hardcoded in Script Include | Low | 20 | Dev-editable, no admin UI
Admin config (§17) | ageing_critical | Ageing-to-Critical hours | — | None | 0 | Absent
Admin config (§17) | analyst_client_map | Alphabet-wise CP-to-analyst map (Manager) | — | None | 0 | Absent
Admin config (§17) | polling_interval | Mailbox polling interval | — | None | 0 | Absent
AI decision quality (§16) | FR-AIQ-001/002 | Confidence thresholds per gate/product, configurable | — | None | 0 | No thresholds
AI decision quality (§16) | FR-AIQ-004 | No auto-settlement regardless of confidence (100% HITL) | Every cashflow confirmed by analyst | Done | 100 | Matches BRD
AI decision quality (§16) | FR-AIQ-010/011 | Drift detection (override spikes, confidence drop) | — | None | 0 | Not implemented
AI decision quality (§16) | BRD 11.4 | AI performance metrics (classifier/extractor/matcher) | AI-vs-deterministic 'Match' Y/N signal (OTC AI dashboard) | Low | 20 | Building block only
Integrations (§12) | INT-001 | Outlook / Exchange (read + tag write) | Mock .eml drop | None | 0 | No Graph/EWS integration
Integrations (§12) | INT-002 | NEWS (read + write-back) | — | None | 0 | No NEWS integration
Integrations (§12) | INT-003 | PCM (read cashflow + write status) | Seeded booking table stands in for PCM read | Partial | 45 | Read mocked; no write
Integrations (§12) | INT-004 | Eve / RDM (counterparty master + alias) | Local counterparty directory (EVE-like) | Partial | 45 | Local stand-in, not live Eve
Integrations (§12) | INT-005 | Takara (credit compliance + holiday calendars) | — | None | 0 | Not integrated
Integrations (§12) | INT-006 | Chinou API (all AI inference) | ServiceNow Now Assist skills used instead | Substitute | 60 | Equivalent AI stack, not Chinou
Integrations (§12) | INT-007 | RBAC / SSO (auth + roles) | ServiceNow auth | Partial | 45 | No Nomura SSO role mapping
Integrations (§12) | INT-008 | Audit log store | Native platform + gen-AI log | Partial | 45 | Not the extended audit framework
NFR / Errors | NFR-004 | Failure isolated to affected cashflow (no queue block) | Per-cashflow processing | Partial | 45 | Basic isolation
NFR / Errors | ERR-002 | Extraction failure → cashflow tagged ERROR, manual handling | Best-effort skip on bad file | Partial | 45 | No ERROR queue state
NFR / Errors | ERR-003/005 | Settlement-system / write-back failure handling | — | None | 0 | No settlement integration to fail
NFR / Errors | NFR-006/007 | Data residency + secrets in vault | Runs in Nomura ServiceNow instance | Partial | 45 | No explicit secrets/residency controls
SHEET COMPLETION (avg of in-scope tasks; Deferred/N-A excluded): |  |  |  |  | 22%
Tasks listed: 37 (in-scope scored: 37)